## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
0 | As an unauthorized user I want create a new account so I can buy and sell items. | 1 | H | IP | 2
1 | As an unauthorized user I want to login my account so that I can access my info. | 1 | H | IP | 1
2 | As an authorized user I want to logout of my account so that a stranger cannot use my account | 1 | H | IP | 1
3 | As an unauthorized user I want to use my google account so that I can use one of my own existing accounts. | 1 | H | IP | 2
4 | As an unauthorized user I want to use my Facebook account so that I can use one of my own existing accounts. | 2 | H | W | 2
5 | As a seller, I want to be able to sell my items in my local area so that relevant buyers can find my items. | 2 | H | W | 3
6 | As a new student, I want to be able to navigate over to the book section so that I can buy textbooks for my classes. | 2 | H | W | 1
7 | As a student looking for an apartment, I want to sort the apartment offerings by price so that I can find an apartment that I can afford easily. | 2 | M | W | 2
8 | As a landlord, I want to advertise one of my apartments on the apartment section so that students can find and rent my apartment. | 3 | M | W | 3
9 | As a student looking to sell my textbook, I want to list last year's textbooks for sale so that I can get some money for them. | 4 | M | W | 4
10 | As a student looking to sell my textbook, I want a list of how much users paid for this textbook last semester so I can make money. | 5 | M | W | 5
11 | As a student selling items, I want to edit the tags on my listing so that they can get better exposure. | 6 | M | W | 6
12 | As a student looking for furniture, I want to use CSwap and navigate to the furniture section so that I can find furniture for my apartment. | 7 | M | W | 7
13 | As a student looking for furniture, I want to sort the furniture section so that I can find only what I need. | 8 | M | W | 8
14 | As a seller, I want to list my calculator for sale under the electronics section so that other students can buy it. | 9 | M | W | 9
15 | As a user, I want a profile so that I can see what the person I am selling to looks like. | 10 | M | W | 10
16 | As a seller, I want to add new photos to my listing so that my listing is more attractive. | 11 | M | W | 11
17 | As a user, I want to delete my account so that I am no longer active on the app. | 12 | M | W | 12
18 | As a seller, I want to change the description of my listing so that It’s available for both pick up and for delivery. | 13 | M | W | 13
19 | As a landlord, I want to be able to list my apartment under multiple colleges so that my apartment will be seen by people in the area. | 14 | M | W | 14
20 | As a seller, I want to be able to see all the items I am currently selling so that I know from organizational purposes. | 15 | M | W | 15
21 | As a seller, I want to see how long my listing has been on the website so that I can determine if I need to make a change to the listing. | 16 | M | W | 16
22 | As a user, I want to be able to give ratings to a seller so that I can help provide useful feedback on the buying process. | 17 | M | W | 17
23 | As a user, I want to be able to see my recently viewed listings so that I can go back to view listings I previously visited. | 18 | M | W | 18
24 | As a student, I want to be able to have a book condition tag so that I can sell my high-quality books for more money. | 19 | M | W | 19
25 | As a student user, I want to filter out listings above a price range so I don't only see listings I can't afford. | 20 | M | W | 20