## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
0 | As an unauthorized user I want create a new account so I can buy and sell items. | 2 | H | IP | 2
1 | As an unauthorized user I want to login to my account so that I can access my info. | 2 | H | IP | 2
2 | As an authorized user I want to logout of my account so that a stranger cannot use my account. | 2 | H | IP | 1
3 | As an unauthorized user I want to login with my Google account so that I can use one of my own existing accounts. | 2 | H | W | 1
4 | As an unauthorized user I want to login with my Facebook account so that I can use one of my own existing accounts. | 2 | H | W | 1
5 | As an authorized user I want to navigate to a book section so that I can buy books. | 3 | H | W | 3
6 | As an authorized user I want to be able to create a listing so that other users can see my books. | 3 | H | W | 2
7 | As an authorized user I want to navigate to a lease section so that I can buy leases. | 4 | M | W | 2
8 | As an authorized user I want to be able to remove a listing so that I can remove items from sale. | 4 | M | W | 3
9 | As an authorized user I want to be able to navigate to an electronics section so that I can buy electronics. | 5 | M | W | 2
10 | As an authorized user I want to be able to sell my electronics so that I can get money for my electronics. | 5 | M | W | 2
11 | As an authorized user I want to mark as listing as sold so that I can keep track of what I've sold. | 6 | M | W | 3
12 | As an authorized user I want to list furniture so that I can sell furniture I no longer need. | 6 | M | W | 2
13 | As an authorized user I want to be able to filter books by their ISBN Number. | 7 | M | W | 3
14 | As an authorized user I want to be able to filter all listings by key terms. | 7 | M | W | 3
15 | As an authorized user I want to add tags to my listing so it can be found easier. | 7 | M | W | 3
16 | As an authorized user I want to add photos to my listings so that it is more likely to be sold. | 8 | M | W | 3
17 | As an authorized user I want to sort listings by ratings so that I can find the best sellers. | 8 | M | W | 2
18 | As an authorized user I want to be able to message the seller so that I can talk with them about the product | 9 | M | W | 3
19 | As an authorized user I want to be able to bookmark listings so that I can return to them easier. | 9 | M | W | 2
20 | As a poor authorized user I want to be able to sort books by quality so that I can buy the cheapest books. | 10 | M | W | 2
21 | As an authorized user, I want to create a profile so that I can see what the person I am selling to looks like. | 10 | M | W | 3
22 | As an authorized user I want to see how many views my listing has so that I can determine if I want to keep it up. | 11 | M | W | 3
23 | As an authorized user I want to be able to block messages from buyers that I do not want to talk to anymore. | 11 | M | W | 2