## Sprint 1 (hidden)
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
0 | As an unauthorized user I want create a new account so I can buy and sell items. | Set up CSwap profile | 2 | Account System | KA, F | 2 | 2 | Landon
1 | As an unauthorized user I want to login to my account so that I can access my info. | Set up CSwap login | 2 | Account System | KA, F | 2 | 2 | Landon, Alex, Michael
2 | As an authorized user I want to logout of my account so that a stranger cannot use my account. | Set up CSwap log out. | 2 | Account System | KA, F | 0.5 | 0.5 | Landon, Alex, Michael
3 | As an unauthorized user I want to login with my Google account so that I can use one of my own existing accounts. | Implement Google account authorization | 2 | Account System | KA, F | 1.5 | 1.5 | Alex
4 | As an unauthorized user I want to login with my Facebook account so that I can use one of my own existing accounts. | Implement Facebook account authorization | 2 | Account System | KA, F | 1.5 | 1.5 | Michael

## Sprint_Backlog_1
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
0 | As an unauthorized user I want create a new account so I can buy and sell items. | Learn about Firebase | 1 | Account System | KA, F | 2 | 0 | Cedric
1 | As an unauthorized user I want to login to my account so that I can access my info. | Learn about Firebase | 1 | Account System | KA, F | 2 | 0 | Cedric, Alex, Michael
2 | As an authorized user I want to logout of my account so that a stranger cannot use my account. | Learn about Firebase | 1 | Account System | KA, F | 0.5 | 0 | Cedric, Alex, Michael
3 | As an unauthorized user I want to login with my Google account so that I can use one of my own existing accounts. | Learn about Google account authorization | 1 | Account System | KA, F | 1.5 | 0.15 | Alex
4 | As an unauthorized user I want to login with my Facebook account so that I can use one of my own existing accounts. | Learn about Facebook account authorization | 1 | Account System | KA, F | 1.5 | 0.15 | Michael

## Sprint_Backlog_2
ID | User Story | Story Tasks | Sprint Number | Sprint Goal
0 | As an unauthorized user I want create a new account so I can buy and sell items. | Set up CSwap profile | 2 | Account System
1 | As an unauthorized user I want to login to my account so that I can access my info. | Set up CSwap login | 2 | Account System
2 | As an authorized user I want to logout of my account so that a stranger cannot use my account. | Set up CSwap log out. | 2 | Account System
3 | As an unauthorized user I want to login with my Google account so that I can use one of my own existing accounts. | Implement Google account authorization | 2 | Account System
4 | As an unauthorized user I want to login with my Facebook account so that I can use one of my own existing accounts. | Implement Facebook account authorization | 2 | Account System

## Sprint_Backlog_3
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
5 | As an authorized user I want to navigate to a book section so that I can buy books. | Navigate to Books | 3 | Listing System | KA, F | 3 | 1.5 | Anthony, Landon
6 | As an authorized user I want to be able to create a listing so that other users can see my books. | Create a listing for books | 3 | Listing System | KA, F | 2 | 1 | Cedric, Anthony

## Sprint_Backlog_4
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
5 | As an authorized user I want to navigate to a book section so that I can buy books. | Listing Navigation | 3 | Listing System | F | 3 | 3 | Landon
7 | As an authorized user I want to navigate to a lease section so that I can buy leases. | Listing Navigation | 4 | Listing System | F | 2 | 2 | Landon
9 | As an authorized user I want to be able to navigate to an electronics section so that I can buy electronics. | Listing Navigation | 5 | Listing System | F | 2 | 2 | Landon
10 | As an authorized user I want to be able to sell my electronics so that I can get money for my electronics. | Create Listing | 5 | Listing System | KA, F | 2 | 1 | Anthony
12 | As an authorized user I want to list furniture so that I can sell furniture I no longer need. | Create Listing | 6 | Listing System | KA, F | 2 | 1 | Anthony

## Sprint_Backlog_5
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
5 | As an authorized user I want to be able to create a listing so that other users can buy my items | Post Listing | 5 | listing system | f | 2 | 2 | Anthony
7 | As an authorized user I want to be able to message the seller so that I can talk with them about the product | Message User | 9 | listing system | f | 1 | 1 | Michael
9 | As an authorized user I want to be able to remove a listing so that I can remove an item from sale | Remove Listing | 4 | listing system | f | 1 | 1 | Anthony
10 | As an authorized user I want to sell my electronics so that I can get money for my electronics | Post Listing | 5 | listing system | f | 1 | 1 | Anthony
12 | As an authorized user I want to list furniture so that I can sell firniture I no longer need | Post Listing | 6 | listing system | f | 1 | 1 | Anthony

## Sprint_Backlog_6
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
8 | As an authorized user I want to be able to remove a listing so that I can remove items from sale. | Remove Listing | 6 | listing system | f | 2 | 1 | Anthony
22 | As an authorized user I want to see how many views my listing has so that I can determine if I want to keep it up. | View Counter | 6 | listing system | f | 2 | 1 | Alex
12 | As an authorized user I want to list furniture so that I can sell furniture I no longer need. | Create Listing | 6 | listing system | f | 1 | 1 | Michael
14 | As an authorized user I want to be able to message the seller so that I can talk with them about the product | Message User | 6 | Message system | f | 1 | 0.998 | Michael